## Sheet1
Maryland Association of Future Business Leaders of America (FBLA)
2016-2017 Program of Work
Goal | Task | Responsibility of: | Deadline
Goal One: Increase Membership by at least 7.5%
Current Chapters
1 | a. Write suggestions for recruitment tips for chapters | Each State Officer | June 21st, 2016
| b. Compile recruitment tips | Secretary-Treasurer | June 26th, 2016
| c. Reach out to all chapters (advisers and presidents) in each region individually to discuss recruitment potential within their school and to distribute tips | Regional Vice-Presidents | September 30th, 2016
2 | Redistribute the Maryland FBLA Chapter Information Package based upon the suggestions of the State Officer Team
| a. Adviser Letter | President | August 20th, 2016
| b. Key Dates | Secretary-Treasurer | August 18th, 2016
| c. Customizable Fliers | President | August 20th, 2016
Inactive Chapters
3 | a. Divide out inactive chapters equally among State Officer Team | President | July 31st, 2016
| b. Contact inactive chapters in Maryland, find an educator willing to serve as an FBLA adviser, and ask to reactivate a new chapter and encourage Advisors to join Professional Division. | State Officers (minus Regional Vice Presidents) | September 25th, 2016
New Chapters
4 | a. Choose at least one school that has potential for an FBLA chapter | Each State Officer | August 17th, 2016
| b. President will assign "unchosen" schools equally among officers | President | August 20th, 2016
| b. Contact school administration to find a staff member who would be willing to serve as an FBLA advisor OR reach out to a student to work on getting a chapter started | Each State Officer | September 25th, 2016
| c. Establish at least one new chapter in Maryland FBLA | Each State Officer | October 11th, 2016
Professional Division
5 | Recruit at least five (5) professional division members (at least one per month: September, October, November, December, January) | Each State Officer | 1 per month until January 31st, 2017
Middle Level
6 | Gauge Interest- Reach out to two (2) middle schools to see if they would be interested in starting middle level chapters. | Each State Officer | October 9th, 2016
Goal Two: Increase Communication and FBLA Awareness
State Officer Team
1 | Complete State Officer Monthly Report Form | Each State Officer | 5th Day of Every Month by 10pm
2 | Maintain communication through email (check within 24 hours) and GroupMe | Each State Officer | n/a
3 | Plan/Announce monthly conference calls or Google hangouts with State Officer Team | President | 5th Day of Every Month
Local Chapter Leaders
4 | a. Divide up chapters to contact amongst regional vice presidents | President | July 31st, 2016
5 | b. Contact chapters to verify advisor information, collect chapter president contact information (update information in Google Doc), and introduce yourself | Regional Vice-Presidents | September 16th, 2016
6 | Send all chapter advisers and leaders in region a "Message from your Regional Vice-President" email | Regional Vice-Presidents | once a month
7 | Create a State President video address to be played at Regional Conferences | President | January 10th, 2016
General Members and/or Public
8 | a. Maintain Maryland FBLA Facebook and Twitter Accounts | Reporter-Historian | n/a
| b. Send out live tweets | Reporter-Historian | n/a
9 | Create and maintain regional Facebook pages | Regional Vice-Presidents | post at least once a month
10 | Maintain use of Maryland FBLA snapchat account at all conferences and events | President, Vice-President | n/a
11 | Promote all Maryland FBLA Social Media (Facebook, Twitter, Instagram, Snapchat) | State Officer Team | n/a
Monthly Presidents Newsletter
12 | Continue the publishing of the monthly state newsletter. (start October)
| a. First Draft | Reporter-Historian | 20th of previous month
| b. Preliminary Approval | Vice President | 25th of previous month
| c. Approval | State Officer Advisor | 26th of previous month
| c. Final Approval & Distribution | Board of Directors | 5th of the month
| d. Distribution | Reporter-Historian | 6th of the month
Chapter Visits
13 | Complete at least five (5) chapter visits | Regions 2 & 5 Vice-Presidents | March 1st, 2017
| Complete at least three (3) chapter visits | President, Vice-President, Secretary-Treasurer, Reporter-Historian, Parliamentarian, Region 3 Vice-President | March 1st, 2017
| Complete at least two (2) chapter visits | Regions 1 & 4 Vice-Presidents | March 1st, 2017
| Visit a total of at least fifteen (15) different chapters | State Officer Team | March 1st, 2017
Increase Visibility of Maryland FBLA (aside from Social Media)
Government
14 | a. Update contact information for government officials | Parliamentarian | August 15th, 2016
| b. Write to at least two (2) government officials via email to inform them about FBLA events and accomplishments and how they can help our organization (i.e. judging, attending a conference, etc.) | Regional Vice-Presidents | December 1st, 2016
| c. Have at least one (1) government official in attendance at all Regional Conferences | Regional Vice-Presidents | n/a
News
15 | Submit three (3) articles to Tomorrow’s Business Leader: http://www.fbla-pbl.org/forms/chapter-news/
1. Fall (CTSO Training)
| a. First Draft | Reporter-Historian | September 7th, 2016
| b. Approve First Draft and send to State Officer Advisor | Vice-President | September 8th, 2016
| c. Final Approval | Board of Directors | September 15th, 2016
| d. Submit Article | Reporter-Historian | September 16th, 2016 | Deadline: 9/23/16
2. Winter (Fall Conference)
| a. First Draft | Reporter-Historian | November 6th, 2016
| b. Approve First Draft and Send to State Officer Advisor | Vice-President, State Officer Advisor | November 7th, 2016
| c. Final Approval | Board of Directors | November 14th, 2016
| d. Submit Article | Reporter-Historian | November 15th, 2016 | Deadline: 12/2/16
3. Spring (March of Dimes Signature Chefs, Regional Conferences)
| a. First Draft | Reporter-Historian | February 2nd, 2017
| b. Approve First Draft and Send to State Officer Advisor | Vice-President | February 4th, 2017
| c. Fnal Approval | Board of Directors | Febuary 9th, 2017
| d. Submit Article | Reporter-Historian | February 10th, 2017 | Deadline: 2/17/17
16 | Submit articles to news outlets | State Officer Team | n/a
| a. Compile contact information for Maryland news outlets | Regional Vice-Presidents | August 15th, 2016
| b. Compile list of news outlets provided by regional vice presidents | State Secretary-Treasurer | August 20th, 2016
| c. Contact news outlets to inform them about Maryland FBLA and encourage them to cover a Maryland FBLA conference or event | Each State Officer | n/a
| d. Compile news outlet articles regarding FBLA | Reporter-Historian | TBD
Goal Three: Increase Fundraising
Maryland FBLA
2 | Contact at least five (5) businesses with the Sponsorship Email Template | Each State Officer | January 20th, 2017 | If 5 business then dinner, show, and icecream
2 | a. Each Regional Vice President will organize and conduct a regional community awareness and fundraising event that will raise funds for their respective region. The fundraising event should be held in a central, convenient location for the entire region if possible. The fundraising event will be reviewed and approved by the Board of Directors. | Regional Vice-Presidents | November 1st, 2016
| b. Approval of fundraising event | Board of Directors | December 1st, 2016
| c. Event Completed | Regional Vice-Presidents | Before Regional Conference
Local Chapter Fundraising
3 | a. Write suggestions for fundraising tips for chapters | Each State Officer | June 21st, 2016
| b. Compile fundraising tips | Secretary-Treasurer | June 26th, 2016
| c. Reach out to all chapters in each region individually to discuss fundraising potential within their school and to distribute fundraising tips | Regional Vice-Presidents | September 30th, 2016
Goal Four: Launch Programs to Unify Maryland FBLA
State Level
1 | Statewide Event: Wizards Day | State Officer Team | December 16th, 2016
| a. Complete Event | State Officer Team | December 16th, 2016
2 | Entrepreneur Workshop and "incubator" by Blue Ocean | Reporter Historian | TBD
3 | Create an online member center to help provide resources for MDFBLA members. | Each State Officer | Ongoing
| a. Divide up resources among state officers | Each State Officer | August 15th, 2016
| b. Submit idea proposals and due dates to Board of Directors for approval. | Vice President | August 20th, 2016
| c. Submit to Vice President for final edits | Each State Officer | Ongoing
| d. Submit resources to Board of Directors for final approval. | Vice President | Ongoing
| e. Upload resources to Maryland FBLA website. | Reporter-Historian, Vice President | Ongoing
Goal Five: Support the National FBLA Programs
1 | Complete the BAA Future Achievement Award | Each State Officer | October 30th, 2016
| Complete the BAA Business Award | Each State Officer | January 5th, 2017
| Complete the BAA Leader Award | Each State Officer | March 1st, 2017
| Complete the BAA America Award | President, Vice-President, Region 4 Vice-President | April 25th, 2017
2 | Recruit at least two (2) members to complete at least the BAA Future Award | Each State Officer | December 1st, 2016
3 | Complete the CSA Community Award | Each State Officer | March 1st, 2017
4 | Encourage members to attend NLC in Anaheim, CA | State Officer Team | n/a
| a. Increase Awareness of and Encourage Raising Funds for March of Dimes | State Vice-President | n/a
Goal Six: Reflection and Transition
2 | Compile Meeting Minutes in binder for next year's team | Secretary-Treasurer | after minutes approved
3 | Create a contact list of all judges, speakers, and workshop presenters invited to the Regional Conference | Regional Vice-Presidents | after Regional Conferences